## Slide 1: Engineering Team Quarterly Report
People Operations Team — Q1 2026 Review

## Slide 2: Project Status Summary
Total projects: 5
Active: 2 (Project Alpha, Project Gamma)
Completed: 1 (Project Beta)
On Hold: 1 (Project Delta)
Planning: 1 (Project Epsilon)

## Slide 3: Survey Results - Average Scores
Leadership: 3.500
Workload: 3.500
Communication: 3.625
Growth: 3.500

## Slide 4: Key Findings
Communication scored highest (3.625) — team practices are working.
Leadership, Workload, Growth all tied at 3.5 — moderate satisfaction.
All four dimensions cluster near the midpoint, indicating no severe pain points.
5 projects across Active / Completed / On Hold / Planning statuses.

## Slide 5: Recommendations
Investigate Workload distribution to address moderate scores.
Boost growth opportunities (training budget, mentorship program).
Review On Hold project (Project Delta) for stakeholder alignment.
Recommendation: schedule follow-up survey in 90 days to track impact.